## Ad-hoc
Feature Name | Description | Team | Area | Pri | Dev FC Weeks | Dev FC Weeks Remaing 4/30 | QA FC Weeks | Column1 | Milesone | Costed By | New Milestone | Dev | Comments
Complete implementation of exisiting F# language | All the work needed to make the F# compiler correctly compile the spec'd F# language. | F# | Compiler | 0 | 16 | 2 | 25 |  | CTP |  |  | dsyme
Language Service Parity with Research Release | Realistically includes more than the research release | F# | IDE support | 0 | 12 | 14 | 12 |  | CTP |  |  | jomof
Project/Item Templates | Create all meaningful templates that don't erqurie any additional work. Low hanging fruit. | F# | IDE support | 0 | 2 | 0.5 | 1 |  | CTP |  |  | lukeh
Language Specification | Write the language spec. | F# | Language | 0 | 4 | 4 | 2 |  | CTP |  |  | dsyme
OCaml Compat | Have a well-designed story for Ocaml compat. Including language/compiler/libraries. | F# | Language | 0 | 4 | 1 | 4 |  | CTP |  |  | dsyme
Complete implementation of exisiting F# libraries | Includes writing general spec. Have a story for consupmtion of libraries in other languages. | F# | Libraries | 0 | 6 | 2 | 12 |  | CTP |  |  | dsyme
F# SDK (essentially same as research release) | Note: Includes VS Add-In. Deployable to Mono(.zip)?? [Something has to be] | F# | Setup/Release | 0 | 4 | 2 | 4 |  | CTP |  |  | jamarg
PowerPack on CodePlex | Put it on CodePlex. Do a pass to clean code up. | F# | SDK Tools | 0 | 1 | 4 | 0 |  | CTP |  |  | dsyme
Globalization | Test + bug fix only. Sanity for CTP, maybe more for RTM. | F# | Setup/Release | 1 | 1 | 1 | 0.5 |  | CTP |  |  | jomof
Migration users from Research to DevDiv F# release | Project migration, maybe more… This now means just a blog released migration tool. We should re-cost. | F# | Setup/Release | 2 | 5 | 1 | 0 |  | CTP |  |  | chrsmith
Project System Parity with Reseach Release |  | F# | IDE Support | 0 | 13 | 13 | 13 |  | CTP |  |  | brianmcn
High-Priority Language Improvements | Next iteration of language innovation. | F# | Language | 0 | 8 | 8 | 0 |  | CTP |  |  | dsyme
(dev) Improve Testability | Type inference testability in particular. | F# | Compiler | 2 | 2 | 2 | 2 |  | CTP |  |  | dsyme
AppBuilding | Spend time appbuilding | F# | Misc | 1 |  | 5 |  |  | CTP |  |  | chrsmith
Complete implemenation of existing F# language (GoLive work) | All the work needed to make the F# compiler correctly compile the spec'd F# language. | F# |  | 0 | 0 | 2 | 16 |  | GoLive |  | Dev10 | dsyme
Breakpoints & Stepping | Define and emit correct PDB spans, IL, and debugger attributes. Try to emulate C#. | F# | Debugger | 0 | 4 | 4 | 8 |  | GoLive |  | CTP | jamarg
F# Libraries Improvements | Address preformance issue. Work on Quotations API. | F# | Libraries | 0 | 6 | 4 | 6 |  | GoLive |  | CTP | dsyme
Security Reviews | Security reviews of all F# components. Threat models. FxCop and other static analysis. | F# | Quality Gates | 0 | 2 | 2 | 2 |  | GoLive |  | CTP | lukeh
Clean up F# SDK Setup | Ship the right stuff :-) | F# | Setup/Release | 0 | 2 | 1 | 0 |  | GoLive |  | CTP | jamarg
Target 64-bit | Only required for runtime (librarires, compiler). May need compiler flags. | F# | Setup/Release | 0 | 4 | 2 | 0 |  | GoLive |  | Dev10 | jamarg
Lite F# Documentation Content | Reference docs for lanugage and libraries. Maybe some conceptual docs. | F# | Documentation | 0 | 5 | 3 | 5 |  | GoLive |  | Dev10 | lukeh
Full Core Project System | TODOs, icons, unit tests, vshost perf, loc/glob, sample-out basic extensibility, review existing code base borrowed from Py, probably a lot of other undiscovered work | F# | IDE support | 0 | 13 | 13 | 12 |  | GoLive |  | CTP | brianmcn
Release Compiler on CodePlex | This may need to include conformance tests | F# | Setup/Release | 1 | 3 | 3 | 0 |  | GoLive |  | CTP | dsyme
Get a Logo |  | F# | Setup/Release | 1 | 1 | 1 | 0 |  | GoLive |  | CTP | jamarg
Language and Libraries Performance and Stress Min Bar | Create perf tests. Measure continuously. Make necessary significant performance enhancements. Work with CLR to get changes which will improve F# runtime perf. | F# | Compiler | 1 | 4 | 4 | 0.5 |  | GoLive |  | Dev10 | dsyme
Compiler Performance and Stress Min Bar | fsc performance. Startup performance. | F# | Compiler | 1 | 4 | 4 | 0.5 |  | GoLive |  | Dev10 | dsyme
Compiler Error Message Improvement | Improve error messages. New warnings. Report an example for incomplete match. Etc. | F# | Compiler | 1 | 3 | 5 | 4.5 |  | GoLive |  | CTP | dsyme | Don: Should this cost be higher? Seems we already have a lot of bug backlog here and there seems to be an increasing stream of these incoming.
Compiler Switches | Add new compiler switches. Standardize with other .NET compilers. | F# | Compiler | 1 | 4 | 4 | 6 |  | GoLive |  | Dev10 | dsyme
Improve FSI | Better pretty printing. New functions for the interactive for state inspection. VS features like, copy/paste, interrupt, dock, resize, etc. | F# | IDE support | 1 | 6 | 6 | 6 |  | GoLive |  | CTP | jamarg | Need to spec
Tolerant Intellisense | Significantly improved error recovery. Users "trust" intellisense. | F# | IDE support | 1 | 8 | 8 | 24 |  | GoLive |  | Dev10 | jomof | Need to figure out what work is involved - is it just patching bugs, or is it re-architecture?
FXCop with F# User Code | Ensure that FXCop can meaningfully be used with F# | F# | IDE Support | 1 | 4 | 3 | 8 |  | GoLive |  | Dev10 | jomof
Basic Editor Features | Navigation, outlining, formatting, Tools¦Options, TODO support | F# | IDE support | 1 | 10 | 21 | 10 |  | GoLive |  | CTP | jomof | Need to break out Tools¦Options
Single File "project"s | Including designging path from single file to fullblown | F# | IDE support | 1 | 4 | 3 | 4 |  | GoLive |  | CTP | brianmcn | LangService has concept already, ought to work; need to work out UI/focus details of project system and debugger
F# Libraries Debuggability | Improve debug display of F# library types | F# | Libraries | 1 | 2 |  | 1 |  | GoLive |  | Dev10 | dsyme
Enable great first time learning experience | Samples/QuickTour/web experience/books/etc. We should have a story and a set of assets. | F# | Documentation | 1 | 5 |  | 5 |  | GoLive |  | CTP | lukeh
Officially support F# SDK + VS Shell combo | Test + bug fix only. | F# | Setup/Release | 1 | 2 |  | 4 |  | GoLive |  |  | jamarg
Put tests on CodePlex | This is a potential means to address Mono testing. | F# | Setup/Release | 1 | 0 |  | 2 |  | GoLive |  |  | chrsmith
(dev) Source code cleanup |  | F# | Compiler | 2 | 2 |  | 0 |  | GoLive |  |  | dsyme
Enable debugging in FSI |  | F# | Debugger | 2 | 4 |  | 8 |  | GoLive |  |  | jamarg
Support Silverlight | This could involve work across the libraries, compiler, project system | F# | IDE support | 2 | 4 |  | 15 |  | GoLive |  |  | dsyme
FSI runs as 64 bit process |  | F# | IDE support | 1 | 5 | 2 | 0.25 |  | GoLive |  |  | jamarg | Priority should probably be lowered - it probably shouldn't be the deafult
(dev) Be Localizable |  | F# | Localization | 0 | 3 |  | 4 |  | Dev10 |  |  | jomof
(dev) Intergate into DevDiv | Source code, test infrastructure, everything else | F# | Setup/Release | 0 | 2 |  | 2 |  | Dev10 |  |  | jomof
Localize to VS Languages | Would have to go to localization team. | F# | Localization | 0 | 0 |  | 0 |  | Dev10 |  |  | jomof
Move to new Editor | Either use the new editor interfaces directly, or move to an MPF shim. The cost here is if we have to do everything. It willl be lower of we get support from VSCore. | F# | IDE support | 0 | 8 |  | 3 |  | Dev10 |  |  | jomof
Quality Gates for Exisiting Features | Need to list work items. FxCop, Code Coverage, Perf plan, Security, API design review, test plans, specs. | F# | Setup/Release | 0 | 4 |  | 7 |  | Dev10 |  |  | jomof
Integrate into VS10 |  | F# | Setup/Release | 0 | 8 |  | 0 |  | Dev10 |  |  | jomof
Integrate into .NET Frameworks | If we don't do this we'll need to build a redist. Includes integrating compilers, libraries, msbuild tasks and targets | F# | Setup/Release | 0 | 4 |  | 0 |  | Dev10 |  |  | dsyme
WinForms designer |  | F# | IDE support | 1 | 7 |  | 7 |  | Dev10 |  |  | jomof
WPF Project Support |  | F# |  | 1 | 6 |  | 6 |  | Dev10 |  |  | jomof
Web Site project support | Without embedded F# code. | F# | IDE support | 1 | 5 |  | 10 |  | Dev10 |  |  | jomof
Full MSDN library documentation and integration | Author full MSDN docs for libraires: Summary, Paramater info, examples, exception information, etc. Cost on UE. Dev cost is for reviews. | F# | Documentation | 1 | 2 |  | 2 |  | Dev10 |  |  | lukeh
Move to use Parallel Framework | For Async, etc. | F# |  | 1 | 1 |  | 2 |  | Dev10 |  |  | dsyme
Advanced Debugging: F# Expression Evaluator and Debugger Windows | Improve display of variable names. Ensure that F# expressions can be typed in debugger windows. Make sure variables are in scope when expected. Support debugger datatips, and other debug-time IDE features. | F# | Debugger | 1 | 6 |  | 12 |  | Dev10 |  |  | jamarg
F1 for Help | The language service should support pushing an F1 context so that F1 goes to the help docs for the correct member/overload/etc. | F# | IDE support | 1 | 1 |  | 1 |  | Dev10 |  |  | jomof
Be part of managed langauge hosting in Office | Enable hosting of F# in Office - leverage other work across VS Lang group. | F# | IDE support | 1 | 10 |  | 15 |  | Dev10 |  |  | jamarg
Support new CLR binder | fsc.exe /versionmanifest:foo.xml /outputmanifest:bar.xml | F# | Compiler | 1 | 2 |  | 2 |  | Dev10 |  |  | dsyme
Support VS Code Generators | XSD, Resources, Settings, WSDL, LINQ to SQL, etc. | F# | IDE support | 2 | 8 |  | 8 |  | Dev10 |  |  | jomof
Class View/Object Browser support F#-style display | IVSLibrary. This cost may be higher due to need to integrate into new Object Browser | F# | IDE support | 2 | 4 | 4 | 6 |  | Dev10 |  |  | brianmcn | I haven't looked at this much, but previous estimate looks plausible
WPF project support | WPF Designer. Support the various WPF project types | F# | IDE support | 2 | 4 | 4 | 4 |  | Dev10 |  |  | brianmcn | I haven't looked at this much, but previous estimate looks plausible
Advanced Editor Features | Refactoring (for instance - turn into #light), Cut from non-#light to #light. | F# | IDE support | 2 | 40 |  | 60 |  | Dev10 |  |  | jomof
Move Project System from Orcas to Dev10 | Support multitargeting (2.0, 3.0, 3.5, and .NET 4.0) | F# | IDE support | 2 | 2 | 2 | 2 |  | Dev10 |  |  | brianmcn
Move to new shared Interactive Window | No separate F# Interactive window, just use the new common VS Interactive window. May require executing on top of CLR instead of current LCG strategy. | F# | IDE support | 2 | 12 |  | 4 |  | Dev10 |  |  | jomof
Class Designer support |  | F# | IDE support | 3 | 8 | 8 | 8 |  | Dev10 |  |  | brianmcn | I haven't looked at this much, but previous estimate looks plausible
Enable 3rd Party F# Tooling | An F# language model and hooks to build refactorings, tools, etc. The ability to build a 3rd party F# IDE. Extensibility hooks in FSI. | F# | IDE support | 3 | 6 |  | 6 |  | Dev10 |  |  | jomof
Intellisense in Web Sites |  | F# | IDE support | 3 | 5 |  | 5 |  | Dev10 |  |  | jomof
F# Redist | Create an F# redist MSI and integrate into DevDiv Release process as well as into a pre-req for Dev10. Likely includes creating multiple versions - for targeting .NET 2.0 and .NET4.0. | F# | Setup/Release | 0 |  | 1 |  |  | Dev10 |  |  | jamarg

## Older
Feature Name | Description | Team | Area | Sub Area | Pri | Sub-Pri | Ideal Days | Confidence | Upper Bound | Calculated Ideal Cost | Ideal To Real | Real Days | FC Mult | FC Days | Dev FC Weeks | QA FC Weeks | Status | Costed By | Dev
Complete implementation of exisiting F# language | All the work needed to make the F# compiler correctly compile the spec'd F# language. | F# | Compiler |  | 0 |  | 5 | 75% | 10 | 6.25 | 0.6 | 10.4167 | 3 | 31.25 | 16 | 25 | CTP |  | dsyme
Complete testing of existing F# language | Catch up on testing the full language. |  |  |  | 0 | [9 empty] | 0 | 16 | GoLive
Language Service Parity with Research Release | Realistically includes more than the research release | F# | IDE support |  | 0 |  |  | 50% |  | 0 | 0.6 | 0 | 3 | 0 | 12 | 12 | CTP |  | jomof
Basic Project System | Basic MSBuild-based project system. May only support editing project files by hand. Provides required services for VS consumers. | F# | IDE support |  | 0 |  | 5 | 25% |  | 0.625 | 0.6 | 1.0417 | 3 | 3.125 | 12 | 12 | CTP |  | jomof
Project/Item Templates | Create all meaningful templates that don't erqurie any additional work. Low hanging fruit. | F# | IDE support |  | 0 |  |  | 75% |  | 0 | 0.6 | 0 | 3 | 0 | 2 | 1 | CTP |  | lukeh
Language Specification |  | F# | Language |  | 0 |  |  | 50% |  | 0 | 0.6 | 0 | 3 | 0 | 4 | 2 | CTP |  | dsyme
OCaml Compat | Have a well-designed story for Ocaml compat. Including language/compiler/libraries. | F# | Language |  | 0 |  |  | 75% |  | 0 | 0.6 | 0 | 3 | 0 | 4 | 4 | CTP |  | dsyme
Complete implementation of exisiting F# libraries | Includes writing general spec. Have a story for consupmtion of libraries in other languages. | F# | Libraries |  | 0 |  |  | 50% |  | 0 | 0.6 | 0 | 3 | 0 | 6 | 12 | CTP |  | jamarg
F# SDK (essentially same as research release) | Note: Includes VS Add-In. Deployable to Mono(.zip)?? [Something has to be] | F# | Setup/Release |  | 0 |  |  | 25% |  | 0 | 0.6 | 0 | 3 | 0 | 4 | 4 | CTP |  | jamarg
Remove FSLex/FSYacc from F# SDK | Put it on CodePlex. Do a pass to clean code up. | F# | SDK Tools |  | 0 |  |  | 50% |  | 0 | 0.6 | 0 | 3 | 0 | 1 | 0 | CTP |  | dsyme
High-Priority Language Improvements | Next iteration of language innovation. | F# | Language |  | 0 |  |  | 75% |  | 0 | 0.6 | 0 | 3 | 0 | 8 | 0 | CTP |  | dsyme
Language Service performance and scalability |  | F# | IDE support |  | 0 |  |  | 50% |  | 0 | 0.6 | 0 | 3 | 0 | 6 | 1 | CTP |  | jomof
Globalization | Test + bug fix only. Sanity for CTP, maybe more for RTM. | F# | Setup/Release |  | 1 |  |  | 50% |  | 0 | 0.6 | 0 | 3 | 0 | 1 | 0.5 | CTP |  | jomof
Migration users from Research to DevDiv F# release | Project migration, maybe more… This now means just a blog released migration tool. We should re-cost. | F# | Setup/Release |  | 2 |  |  | 25% |  | 0 | 0.6 | 0 | 3 | 0 | 5 | 0 | CTP |  | jomof
(dev) Improve Testability | Type inference testability in particular. | F# | Compiler |  | 2 |  |  | 75% |  | 0 | 0.6 | 0 | 3 | 0 | 2 | 2 | CTP |  | dsyme
Breakpoints & Stepping | Define and emit correct PDB spans, IL, and debugger attributes. Try to emulate C#. | F# | Debugger |  | 0 |  |  | 50% |  | 0 | 0.6 | 0 | 3 | 0 | 4 | 8 | GoLive |  | jamarg
F# Libraries Improvements | Address preformance issue. Work on Quotations API. | F# | Libraries |  | 0 |  |  | 25% |  | 0 | 0.6 | 0 | 3 | 0 | 6 | 6 | GoLive |  | jamarg
Security Reviews | Security reviews of all F# components. Threat models. FxCop and other static analysis. | F# | Quality Gates |  | 0 |  |  | 25% |  | 0 | 0.6 | 0 | 3 | 0 | 2 | 2 | GoLive |  | jomof
Clean up F# SDK Setup | Ship the right stuff :-) | F# | Setup/Release |  | 0 |  |  | 50% |  | 0 | 0.6 | 0 | 3 | 0 | 2 | 0 | GoLive |  | jamarg
Target 64-bit | Only required for runtime (librarires, compiler). May need compiler flags. | F# | Setup/Release |  | 0 |  |  | 25% |  | 0 | 0.6 | 0 | 3 | 0 | 4 | 0 | GoLive |  | jamarg | Don: What is the 4 weeks here for? Seems this is just adding a flag and flipping a bit in the binary
Lite F# Documentation Content | Reference docs for lanugage and libraries. Maybe some conceptual docs. | F# | Documentation |  | 0 |  |  | 25% |  | 0 | 0.6 | 0 | 3 | 0 | 5 | 5 | GoLive |  | lukeh
Full Core Project System | Resolve file ordering in a satisfying way. Support Source Control. Other work to complete the core development scnearios fo rht projhect system. | F# | IDE support |  | 0 |  |  | 50% |  | 0 | 0.6 | 0 | 3 | 0 | 8 | 12 | GoLive |  | jomof
Release Compiler on CodePlex | This may need to include conformance tests | F# | Setup/Release |  | 1 | 1.1 |  | 50% |  | 0 | 0.6 | 0 | 3 | 0 | 3 | 0 | GoLive |  | jomof
Put FSLex/FSYacc on CodePlex |  | F# | SDK Tools |  | 1 | 1.1 |  | 50% |  | 0 | 0.6 | 0 | 3 | 0 | 2 | 0 | GoLive |  | dsyme
Get a Logo |  | F# | Setup/Release |  | 1 | 1.1 |  | 75% |  | 0 | 0.6 | 0 | 3 | 0 | 1 | 0 | GoLive |  | jamarg
FSI runs as 64 bit process |  | F# | IDE support |  | 1 | 1.2 |  | 25% |  | 0 | 0.6 | 0 | 3 | 0 | 5 | 0.25 | GoLive |  | jamarg
Language and Libraries Performance and Stress Min Bar | Create perf tests. Measure continuously. Make necessary significant performance enhancements. Work with CLR to get changes which will improve F# runtime perf. | F# | Compiler |  | 1 | 1.2 |  | 50% |  | 0 | 0.6 | 0 | 3 | 0 | 4 | 0.5 | GoLive |  | dsyme
Compiler Performance and Stress Min Bar | fsc performance. Startup performance. | F# | Compiler |  | 1 | 1.2 |  | 50% |  | 0 | 0.6 | 0 | 3 | 0 | 4 | 0.5 | GoLive |  | dsyme
Compiler Error Message Improvement | Improve error messages. New warnings. Report an example for incomplete match. Etc. | F# | Compiler |  | 1 | 1.1 |  | 75% |  | 0 | 0.6 | 0 | 3 | 0 | 3 | 4.5 | GoLive |  | jomof | Don: Should this cost be higher? Seems we already have a lot of bug backlog here and there seems to be an increasing stream of these incoming.
Compiler Switches | Add new compiler switches. Standardize with other .NET compilers. | F# | Compiler |  | 1 | 1.2 |  | 75% |  | 0 | 0.6 | 0 | 3 | 0 | 4 | 6 | GoLive |  | dsyme
Improve FSI | Better pretty printing. New functions for the interactive for state inspection. VS features like, copy/paste, interrupt, dock, resize, etc. | F# | IDE support |  | 1 | 1.2 |  | 25% |  | 0 | 0.6 | 0 | 3 | 0 | 6 | 6 | GoLive |  | jomof
Tolerant Intellisense | Significantly improved error recovery. Users "trust" intellisense. | F# | IDE support |  | 1 | 1.1 |  | 25% |  | 0 | 0.6 | 0 | 3 | 0 | 8 | 24 | GoLive |  | jomof
FXCop with F# User Code | Ensure that FXCop can meaningfully be used with F# | F# | IDE Support |  | 1 | 1.2 |  | 25% |  | 0 | 0.6 | 0 | 3 | 0 | 4 | 8 | GoLive |  | jomof
Basic Editor Features | Navigation, outlining, formatting, Tools¦Options, TODO support | F# | IDE support |  | 1 | 1.2 |  | 25% |  | 0 | 0.6 | 0 | 3 | 0 | 10 | 10 | GoLive |  | jomof
Single File "project"s | Including designging path from single file to fullblown | F# | IDE support |  | 1 | 1.1 |  | 50% |  | 0 | 0.6 | 0 | 3 | 0 | 4 | 4 | GoLive |  | jomof
F# Libraries Debuggability | Improve debug display of F# library types | F# | Libraries |  | 1 | 1.2 |  | 50% |  | 0 | 0.6 | 0 | 3 | 0 | 2 | 1 | GoLive |  | jamarg
Enable great first time learning experience | Samples/QuickTour/web experience/books/etc. We should have a story and a set of assets. | F# | Documentation |  | 1 | 1.1 |  | 50% |  | 0 | 0.6 | 0 | 3 | 0 | 5 | 5 | GoLive |  | lukeh
Officially support F# SDK + VS Shell combo | Test + bug fix only. | F# | Setup/Release |  | 1 | 1.1 |  | 50% |  | 0 | 0.6 | 0 | 3 | 0 | 2 | 4 | GoLive |  | jamarg
Put tests on CodePlex | This is a potential means to address Mono testing. | F# | Setup/Release |  | 1 | 1.1 |  | 25% |  | 0 | 0.6 | 0 | 3 | 0 | 0 | 2 | GoLive |  | chrsmith
(dev) Source code cleanup |  | F# | Compiler |  | 2 |  |  | 75% |  | 0 | 0.6 | 0 | 3 | 0 | 2 | 0 | GoLive |  | dsyme
Enable debugging in FSI |  | F# | Debugger |  | 2 |  |  | 25% |  | 0 | 0.6 | 0 | 3 | 0 | 4 | 8 | GoLive |  | jamarg
Support Silverlight | This could involve work across the libraries, compiler, project system | F# | IDE support |  | 2 |  |  | 25% |  | 0 | 0.6 | 0 | 3 | 0 | 4 | 15 | GoLive |  | jomof
(dev) Be Localizable |  | F# | Localization |  | 0 |  |  | 75% |  | 0 | 0.6 | 0 | 3 | 0 | 3 | 4 | Dev10 |  | jomof
(dev) Intergate into DevDiv | Source code, test infrastructure, everything else | F# | Setup/Release |  | 0 |  |  | 25% |  | 0 | 0.6 | 0 | 3 | 0 | 2 | 2 | Dev10 |  | jomof
Localize to VS Languages | Would have to go to localization team. | F# | Localization |  | 0 |  |  | 75% |  | 0 | 0.6 | 0 | 3 | 0 | 0 | 0 | Dev10 |  | jomof
Move to new Editor | Either use the new editor interfaces directly, or move to an MPF shim. The cost here is if we have to do everything. It willl be lower of we get support from VSCore. | F# | IDE support |  | 0 |  |  | 50% |  | 0 | 0.6 | 0 | 3 | 0 | 8 | 3 | Dev10 |  | jomof
Quality Gates for Exisiting Features | Need to list work items. FxCop, Code Coverage, Perf plan, Security, API design review, test plans, specs. | F# | Setup/Release |  | 0 |  |  | 25% | [6 empty] | 4 | 7 | Dev10 |  | jomof
Integrate into VS10 |  | F# | Setup/Release |  | 0 |  |  | 25% | [6 empty] | 8 | 0 | Dev10 |  | jomof
Integrate into .NET Frameworks | If we don't do this we'll need to build a redist. Includes integrating compilers, libraries, msbuild tasks and targets | F# | Setup/Release |  | 0 |  |  | 25% | [6 empty] | 4 | 0 | Dev10 |  | jomof
WinForms designer |  | F# | IDE support |  | 1 |  |  | 25% |  | 0 | 0.6 | 0 | 3 | 0 | 7 | 7 | Dev10 |  | jomof
WPF Project Support |  | F# |  |  | 1 |  |  | 25% |  | 0 | 0.6 | 0 | 3 | 0 | 6 | 6 | Dev10 |  | jomof
Web Site project support | Without embedded F# code. | F# | IDE support |  | 1 |  |  | 50% |  | 0 | 0.6 | 0 | 3 | 0 | 5 | 10 | Dev10 |  | jomof
Full MSDN library documentation and integration | Author full MSDN docs for libraires: Summary, Paramater info, examples, exception information, etc. Cost on UE. Dev cost is for reviews. | F# | Documentation |  | 1 |  |  | 25% | [6 empty] | 2 | 2 | Dev10 |  | lukeh
Move to use Parallel Framework | For Async, etc. | F# |  |  | 1 |  |  | 50% | [6 empty] | 1 | 2 | Dev10 |  | dsyme
Advanced Debugging: F# Expression Evaluator and Debugger Windows | Improve display of variable names. Ensure that F# expressions can be typed in debugger windows. Make sure variables are in scope when expected. Support debugger datatips, and other debug-time IDE features. | F# | Debugger |  | 1 |  |  | 25% | [6 empty] | 6 | 12 | Dev10 |  | jamarg
F1 for Help | The language service should support pushing an F1 context so that F1 goes to the help docs for the correct member/overload/etc. | F# | IDE support |  | 1 |  |  | 50% | [6 empty] | 1 | 1 | Dev10 |  | jomof
Be part of managed langauge hosting in Office | Enable hosting of F# in Office - leverage other work across VS Lang group. | F# | IDE support |  | 1 |  |  | 25% | [6 empty] | 10 | 15 | Dev10 |  | jamarg
Support new CLR binder | fsc.exe /versionmanifest:foo.xml /outputmanifest:bar.xml | F# | Compiler |  | 1 | [9 empty] | 2 | 2 | Dev10 |  | dsyme
Support VS Code Generators | XSD, Resources, Settings, WSDL, LINQ to SQL, etc. | F# | IDE support |  | 2 |  |  | 25% | [6 empty] | 8 | 8 | Dev10 |  | jomof
Class View/Object Browser support F#-style display | IVSLibrary. This cost may be higher due to need to integrate into new Object Browser | F# | IDE support |  | 2 |  |  | 25% | [6 empty] | 4 | 6 | Dev10 |  | jomof
WPF project support | WPF Designer. Support the various WPF project types | F# | IDE support |  | 2 |  |  | 25% | [6 empty] | 4 | 4 | Dev10 |  | jomof
Advanced Editor Features | Refactoring (for instance - turn into #light), Cut from non-#light to #light. | F# | IDE support |  | 2 |  |  | 25% | [6 empty] | 40 | 60 | Dev10 |  | jomof
Move Project System from Orcas to Dev10 | Support multitargeting (2.0, 3.0, 3.5, and .NET 4.0) | F# | IDE support |  | 2 |  |  | 50% | [6 empty] | 2 | 2 | Dev10 |  | jomof
Move to new shared Interactive Window | No separate F# Interactive window, just use the new common VS Interactive window. May require executing on top of CLR instead of current LCG strategy. | F# | IDE support |  | 2 |  |  | 25% | [6 empty] | 12 | 4 | Dev10 |  | jomof
Class Designer support |  | F# | IDE support |  | 3 |  |  | 25% | [6 empty] | 8 | 8 | Dev10 |  | jomof
Enable 3rd Party F# Tooling | An F# language model and hooks to build refactorings, tools, etc. The ability to build a 3rd party F# IDE. Extensibility hooks in FSI. | F# | IDE support |  | 3 |  |  | 25% | [6 empty] | 6 | 6 | Dev10 |  | jomof
Intellisense in Web Sites |  | F# | IDE support |  | 3 |  |  | 25% | [6 empty] | 5 | 5 | Dev10 |  | jomof
CALCULATIONS
[14 empty] | Dev costs by milestone and priority | [7 empty] | QA costs by milestone and priority
[15 empty] | 0 | 1 | 2 | 3 | Total |  |  | 0 | 1 | 2 | 3 | Total
[14 empty] | CTP | 75 | 1 | 7 | 0 | 83 |  | CTP | 73 | 0.5 | 2 | 0 | 75.5
[14 empty] | GoLive | 31 | 67 | 10 | 0 | 108 |  | GoLive | 49 | 75.75 | 23 | 0 | 147.75
[14 empty] | Dev10 | 29 | 40 | 70 | 19 | 158 |  | Dev10 | 16 | 57 | 84 | 19 | 176
[14 empty] | Total | 135 | 108 | 87 | 19 | 349 |  | Total | 138 | 133.25 | 109 | 19 | 399.25
[14 empty] | Weeks | Headcount
[13 empty] | CTP Weeks | 22 | 3.5
[13 empty] | GoLive | 12 | 5
[13 empty] | Dev10 | 6 | 6
[13 empty] | If we can code in Beta1 | 7 | 6
[15 empty] | Totla: | Pri 1s: | Pri2s
[14 empty] | CTP | -6 | 2 | 1
[14 empty] | GoLive | -48 | 29 | -38
[15 empty] | -122 | 7 | -33
[14 empty] | Dev10 | -80 | 13 | -27
[14 empty] | Extra: |  | 44 | -64
Assumuptions:
We can move CTP to July 13th
We can use Dev10 Beta1 for integration work
Resourcing above is accurate
Outcomes
We can do all p1/p2 for CTP
We can do all p1 plus half of p2 for RTM
We can do all p1 for Dev10, but no additional P2

## Larger Granularity
Project System Improvements
Language Service Improvements
Release | Feature Name | Stack Rank | Description | Pri | Area | Dev % Done | QA % Done | Dev Cost | QA Cost | Team | Dev FC Weeks | Dev FC Weeks Remaing 4/30 | QA FC Weeks | Column1 | Costed By | Dev | QA | Comments
CTP | Language Specification | 1 | Write the language spec. | Bone | Language | 100% | 100% | 4 | 2 | F# | 4 | 4 | 2 |  |  | dsyme
CTP | Complete implementation of exisiting F# language | 2 | F# compiler correctly compiles the spec'd F# language. | Bone | Language | 100% | 30% | 2 | 16 | F# | 16 | 2 | 25 |  |  | dsyme
CTP | Complete implementation of exisiting F# libraries | 3 | Review, implementation and spec. Includes rejection of some parts of research libraries. | Bone | Libraries | 80% | 0% | 2 | 3 | F# | 6 | 2 | 12 |  |  | dsyme
CTP | Basic Project System | 4 | MSBuild, Solution Explorer, Add Reference…, Basic Property Pages, Basic File Ordering | Bone | IDE Support | 60% | 0% | 8 | 9 | F# | 13 | 13 | 13 |  |  | brianmcn
CTP | Basic Language Service | 5 | Colorization, Background Compile, Completion Lists, Quick Info, Parameter Help, F1 Integration, Goto Definition | Bone | IDE support | 80% | 20% | 8 | 8 | F# | 12 | 14 | 12 |  |  | jomof
CTP | Basic Debugging | 6 | Breakpoints,stepping and debugger view windows | Bone | Debugger | 0% | 0% | 4 | 6 | F# | 4 | 4 | 8 |  |  | dsyme
CTP | Basic F# Interactive | 7 | Toolwindow, installs with package, interaction points with editor and project system | Bone | IDE support | 20% | 0% | 6 | 2 | F# | 6 | 6 | 6 |  |  | jamarg |  | Need to spec
CTP | High-Priority Language Improvements | 8 | OO completeness, Operator Overloading consistency, Units of Measure, #light as default, less-order-dependent name resolution | Bone | Language | 50% | 20% | 9 | 5 | F# | 8 | 8 | 0 |  |  | dsyme
CTP | High-priority Libraries Improvements | 10 | Debuggability, Expression Tree <-> Quotation bridge | 90% Confidence | Libraries | 0% | 0% | 4 | 4 | F# | 6 | 4 | 6 |  |  | dsyme
Dev10 | Compiler Error Message Improvement | 9 | Systematic improvement to syntax error reporting. | 90% Confidence | Compiler | 50% | 30% | 5 | 3 | F# | 3 | 5 | 4.5 |  |  | dsyme |  | Don: Should this cost be higher? Seems we already have a lot of bug backlog here and there seems to be an increasing stream of these incoming.
CTP | Project System Improvments | 12 |  | 90% Confidence | IDE support | 0% | 0% | 4 | 5 | F# | 13 | 13 | 12 |  |  | brianmcn
CTP | Language Service Improvements | 11 | Many mini-features: privacy glyphs, colorize pseudo-primitive types, etc. | 90% Confidence | IDE support | 0% | 0% | 4 | 4 | F# | 10 | 21 | 10 |  |  | jomof |  | Need to break out Tools¦Options
CTP | Migration users from Research to DevDiv F# release | 13 | Provide a migration tool from research project files to MSBuild-based project files. | Cut | Setup/Release | 0% | 0% | 1 | 0 | F# | 5 | 1 | 0 |  |  | chrsmith
Dev10 | Quality Gates for Exisiting Features | 1 | Pass all the quality gates for all components shipping in Dev10. | Bone | Setup/Release | 0% | 0% | 9 | 4 | F# | 4 |  | 7 |  |  | jomof
Dev10 | F# Redist | 2 | F# Redist SKU. Two versions, for use with .NET3.5 and .NET4.0 respectively. | Bone | Setup/Release | 0% | 0% | 5 | 2 | F# |  | 1 |  |  |  | jamarg
Dev10 | Integrate into VS10 | 3 | Source and bugs in TFS, builds out of vslang_01 and setup authoring into Dev10 VS Pro+ | Bone | Setup/Release | 0% | 0% | 4 | 2 | F# | 8 |  | 0 |  |  | jomof
Dev10 | Move to new Editor | 4 | Use "new editor" with F# language service. | Bone | IDE support | 0% | 0% | 7 | 5 | F# | 8 |  | 3 |  |  | jomof
Dev10 | Multitargeting | 6 | Support multitargeting (2.0, 3.0, 3.5, and .NET 4.0) | 90% Confidence | IDE support | 0% | 0% | 2 | 2 | F# | 2 | 2 | 2 |  |  | brianmcn
Dev10 | Language and Libraries Perf and Stress Improvements | 7 | Create perf tests. Measure continuously. Make necessary significant performance enhancements. Work with CLR to get changes which will improve F# runtime perf. | 90% Confidence | Compiler | 0% | 0% | 4 | 0 | F# | 4 | 4 | 0.5 |  |  | dsyme
Dev10 | Compiler Perf and Stress Improvements | 8 | fsc performance. Startup performance. | 90% Confidence | Compiler | 0% | 0% | 4 | 0 | F# | 4 | 4 | 0.5 |  |  | dsyme
Dev10 | WinForms designer | 9 |  | Cut | IDE support | 0% | 0% | 7 | 6 | F# | 7 |  | 7 |  |  | jomof
Dev10 | Web Site project support | 10 |  | Cut | IDE support | 0% | 0% | 5 | 10 | F# | 5 |  | 10 |  |  | jomof
Dev10 | WPF Project support | 11 |  | Cut | IDE Support | 0% | 0% | 6 | 6 | F# | 6 |  | 6 |  |  | jomof
Dev10 | WCF Service References | 12 | Add new Service Reference | Cut | IDE Support | 0% | 0% | 6 | 6 | F# | [5 empty] | jomof
Dev10 | Additional Visual F# Interactive Features | 13 | Debuggabitlity | Cut | Debugger | 0% | 0% | 4 | 2 | F# | 4 |  | 8 |  |  | jamarg
Dev10 | Class View/Object Browser support F#-style display | 14 |  | Cut | IDE support | 0% | 0% | 4 | 2 | F# | 4 | 4 | 6 |  |  | brianmcn |  | I haven't looked at this much, but previous estimate looks plausible
Dev10 | Advanced Debugging | 15 | Allow using F# in the immediate window instead of C#. | Cut | Debugger | 0% | 0% | 6 | 7 | F# | 6 |  | 12 |  |  | jamarg
Dev10 | F# Express | 16 | Free F# IDE | Very Cut | Setup/Release | 0% | 0% | ?? | 4 | F# | [5 empty] | jomof
Dev10 | Enable 3rd Party F# Tooling | 17 | An F# language model and hooks to build refactorings, tools, etc. The ability to build a 3rd party F# IDE. Extensibility hooks in FSI. | Very Cut | IDE support | 0% | 0% | 6 | 5 | F# | 6 |  | 6 |  |  | jomof
Dev10 | Silverlight support | 18 | A version of the F# redist that installs on Silverlight, and VS support for targeting it. | Very Cut | Setup/Release | 0% | 0% | 4 | 8 | F# | [5 empty] | dsyme
Dev10 | Advanced Language Service Features | 19 | Refactoring, Navigation, outlining, formatting, Tools¦Options, TODO support | Very Cut | IDE support | 0% | 0% | 60 | 28 | F# | 40 |  | 60 |  |  | jomof
| Advanced Project System Features | 20 |  | Very Cut |  |  |  | 6 | 6
|  |  |  | Costs |  | FC weeks of work |  | Heads
[6 empty] | Dev | QA | Devs | QA
[5 empty] | CTP: | 60 | 67 | 3.5 | 3
[5 empty] | Dev10: | 35 | 15 | 4 | 4
[5 empty] | Total: | 95 | 82
|  |  |  | Needed |  | Dev | QA | Actual
[5 empty] | CTP | 17.1429 | 22.3333 | 12
[5 empty] | Dev10 | 8.75 | 3.75 | 14
[5 empty] | Total | 25.8929 | 26.0833 | 26
Other things we need to track:
UE
Note on C4: Luke Hoban: CTP targetting 9/1. Dev10 M3 complete 11/28. We'll be focused on CTP through 9/1. If we don't get to CTP pri2s or pri3s, we will not do them.
Note on E4: Luke Hoban: Seperately stack ranked for CTP and RTM. CTP is timeboxed to end 9/1.
Note on G4: Luke Hoban: Priority: - 1 = Bone Line - 2 = Current Plan - 3 = Cut - 4 = Very Cut
Note on I4: Luke Hoban: % to code complete.
Note on J4: Luke Hoban: % to test complete
Note on K4: Luke Hoban: Costs in "Feature Crew Weeks". Conversion factor from heads down time is ~ x5. So numbers can also be read as "Heads down coding days".
Note on L4: Luke Hoban: Costs in "Feature Crew Weeks". Conversion factor from heads down time is ~ x5. So numbers can also be read as "Heads down coding days".
Note on I10: Luke Hoban: Should probably say this is 50% done or so….
Note on G15: Luke Hoban: Was 2 - need more data from Brian.
Note on G16: Luke Hoban: Was 2 - need more data from Brian.
Note on G17: Luke Hoban: Was 2 - need more data from Brian.
Note on G25: Luke Hoban: Was 2 - need more data from Brian.
Note on G26: Luke Hoban: Was 2 - need more data from Brian.
Note on G27: Luke Hoban: Was 2 - need more data from Brian.
Note on G28: Luke Hoban: Was 2 - need more data from Brian.
Note on G29: Luke Hoban: Was 2 - need more data from Brian.
Note on G30: Luke Hoban: Was 2 - need more data from Brian.
Note on G31: Luke Hoban: Was 2 - need more data from Brian.

## April
| Feature Name | Stack Rank | Description | Pri | Area | Dev % Done | QA % Done | Dev Cost | QA Cost | Team | Dev FC Weeks | Dev FC Weeks Remaing 4/30 | QA FC Weeks | Column1 | Costed By | Dev | QA | Comments
| Language Specification | 1 | Write the language spec. | Bone | Language | 80% | 100% | 4 | 2 | F# | 4 | 4 | 2 |  |  | dsyme
| Complete implementation of exisiting F# language | 2 | F# compiler correctly compiles the spec'd F# language. | Bone | Language | 80% | 30% | 2 | 16 | F# | 16 | 2 | 25 |  |  | dsyme
| Complete implementation of exisiting F# libraries | 3 | Review, implementation and spec. Includes rejection of some parts of research libraries. | Bone | Libraries | 80% | 0% | 2 | 3 | F# | 6 | 2 | 12 |  |  | dsyme
| Basic Project System | 4 | MSBuild, Solution Explorer, Add Reference…, Basic Property Pages, Basic File Ordering | Bone | IDE Support | 60% | 0% | 8 | 9 | F# | 13 | 13 | 13 |  |  | brianmcn
| Basic Language Service | 5 | Colorization, Background Compile, Completion Lists, Quick Info, Parameter Help, F1 Integration, Goto Definition | Bone | IDE support | 60% | 20% | 8 | 8 | F# | 12 | 14 | 12 |  |  | jomof
| Basic Debugging | 6 | Breakpoints,stepping and debugger view windows | Bone | Debugger | 0% | 0% | 4 | 6 | F# | 4 | 4 | 8 |  |  | dsyme
| Basic F# Interactive | 7 | Toolwindow, installs with package, interaction points with editor and project system | Bone | IDE support | 20% | 0% | 6 | 2 | F# | 6 | 6 | 6 |  |  | jamarg |  | Need to spec
| High-Priority Language Improvements | 8 | OO completeness, Operator Overloading consistency, Units of Measure, #light as default, less-order-dependent name resolution | Bone | Language | 50% | 20% | 9 | 5 | F# | 8 | 8 | 0 |  |  | dsyme
CTP Line
| Quality Gates for Exisiting Features | 10 | Pass all the quality gates for all components shipping in Dev10. | Bone | Setup/Release | 0% | 0% | 9 | 4 | F# | 4 |  | 7 |  |  | jomof
| F# Redist | 11 | F# Redist SKU. Two versions, for use with .NET3.5 and .NET4.0 respectively. | Bone | Setup/Release | 0% | 0% | 5 | 2 | F# |  | 1 |  |  |  | jamarg
| Integrate into VS10 | 12 | Source and bugs in TFS, builds out of vslang_01 and setup authoring into Dev10 VS Pro+ | Bone | Setup/Release | 0% | 0% | 4 | 2 | F# | 8 |  | 0 |  |  | jomof
| Move to new Editor | 13 | Use "new editor" with F# language service. | Bone | IDE support | 0% | 0% | 7 | 5 | F# | 8 |  | 3 |  |  | jomof
Bone Line
| Compiler Error Message Improvement | 14 | Systematic improvement to syntax error reporting. | 90% Confidence | Compiler | 50% | 30% | 5 | 3 | F# | 3 | 5 | 4.5 |  |  | dsyme |  | Don: Should this cost be higher? Seems we already have a lot of bug backlog here and there seems to be an increasing stream of these incoming.
| High-priority Libraries Improvements | 15 | Debuggability, Expression Tree <-> Quotation bridge | 90% Confidence | Libraries | 0% | 0% | 4 | 4 | F# | 6 | 4 | 6 |  |  | dsyme
| Language Service Improvements | 16 | Many mini-features: privacy glyphs, colorize pseudo-primitive types, etc. | 90% Confidence | IDE support | 0% | 0% | 4 | 4 | F# | 10 | 21 | 10 |  |  | jomof |  | Need to break out Tools¦Options
| Project System Improvments | 17 |  | 90% Confidence | IDE support | 0% | 0% | 4 | 5 | F# | 13 | 13 | 12 |  |  | brianmcn
| Multitargeting | 18 | Support multitargeting (2.0, 3.0, 3.5, and .NET 4.0) | 90% Confidence | IDE support | 0% | 0% | 2 | 2 | F# | 2 | 2 | 2 |  |  | brianmcn
| Language and Libraries Perf and Stress Improvements | 19 | Create perf tests. Measure continuously. Make necessary significant performance enhancements. Work with CLR to get changes which will improve F# runtime perf. | 90% Confidence | Compiler | 0% | 0% | 4 | 0 | F# | 4 | 4 | 0.5 |  |  | dsyme
| Compiler Perf and Stress Improvements | 20 | fsc performance. Startup performance. | 90% Confidence | Compiler | 0% | 0% | 4 | 0 | F# | 4 | 4 | 0.5 |  |  | dsyme
Cut Line
| WinForms designer | 21 |  | Cut | IDE support | 0% | 0% | 7 | 6 | F# | 7 |  | 7 |  |  | jomof
| Web Site project support | 22 |  | Cut | IDE support | 0% | 0% | 5 | 10 | F# | 5 |  | 10 |  |  | jomof
| WPF Project support | 23 |  | Cut | IDE Support | 0% | 0% | 6 | 6 | F# | 6 |  | 6 |  |  | jomof
| F# Express | 24 | Free F# IDE | Cut | Setup/Release | 0% | 0% | ?? | 4 | F# | [5 empty] | jomof
| WCF Service References | 25 | Add new Service Reference | Cut | IDE Support | 0% | 0% | 6 | 6 | F# | [5 empty] | jomof
| Additional Visual F# Interactive Features | 26 | Debuggabitlity | Cut | Debugger | 0% | 0% | 4 | 2 | F# | 4 |  | 8 |  |  | jamarg
| Class View/Object Browser support F#-style display | 27 |  | Cut | IDE support | 0% | 0% | 4 | 2 | F# | 4 | 4 | 6 |  |  | brianmcn |  | I haven't looked at this much, but previous estimate looks plausible
| Advanced Debugging | 28 | Allow using F# in the immediate window instead of C#. | Cut | Debugger | 0% | 0% | 6 | 7 | F# | 6 |  | 12 |  |  | jamarg
| Enable 3rd Party F# Tooling | 29 | An F# language model and hooks to build refactorings, tools, etc. The ability to build a 3rd party F# IDE. Extensibility hooks in FSI. | Very Cut | IDE support | 0% | 0% | 6 | 5 | F# | 6 |  | 6 |  |  | jomof
| Silverlight support | 30 | A version of the F# redist that installs on Silverlight, and VS support for targeting it. | Very Cut | Setup/Release | 0% | 0% | 4 | 8 | F# | [5 empty] | dsyme
| Advanced Language Service Features | 31 | Refactoring, Navigation, outlining, formatting, Tools¦Options, TODO support | Very Cut | IDE support | 0% | 0% | 60 | 28 | F# | 40 |  | 60 |  |  | jomof
| Advanced Project System Features | 32 |  | Very Cut | IDE Support |  |  | 6 | 6 | F# | [5 empty] | brianmcn
[17 empty] | Costs |  | FC weeks of work |  | Heads |  | Calendar needed |  | Calendar Actual
[19 empty] | Dev | QA | Devs | QA | Dev | QA
[17 empty] | CTP | CTP: | 43 | 51 | 3.5 | 3 | 12.2857 | 17 | 12
[17 empty] | Dev10 | Dev10: | 52 | 31 | 4 | 4 | 13 | 7.75 | 14
[17 empty] | Total | Total: | 95 | 82 |  |  | 25.2857 | 24.75 | 26
Other things we need to track:
UE
Note on D4: Luke Hoban: Seperately stack ranked for CTP and RTM. CTP is timeboxed to end 9/1.
Note on F4: Luke Hoban: Priority: - 1 = Bone Line - 2 = Current Plan - 3 = Cut - 4 = Very Cut
Note on H4: Luke Hoban: % to code complete.
Note on I4: Luke Hoban: % to test complete
Note on J4: Luke Hoban: Costs in "Feature Crew Weeks". Conversion factor from heads down time is ~ x5. So numbers can also be read as "Heads down coding days".
Note on K4: Luke Hoban: Costs in "Feature Crew Weeks". Conversion factor from heads down time is ~ x5. So numbers can also be read as "Heads down coding days".
Note on H10: Luke Hoban: Should probably say this is 50% done or so….
Note on F21: Luke Hoban: Was 2 - need more data from Brian.
Note on F22: Luke Hoban: Was 2 - need more data from Brian.
Note on F27: Luke Hoban: Was 2 - need more data from Brian.
Note on F28: Luke Hoban: Was 2 - need more data from Brian.
Note on F29: Luke Hoban: Was 2 - need more data from Brian.
Note on F31: Luke Hoban: Was 2 - need more data from Brian.
Note on F32: Luke Hoban: Was 2 - need more data from Brian.
Note on F33: Luke Hoban: Was 2 - need more data from Brian.
Note on F34: Luke Hoban: Was 2 - need more data from Brian.

## M3
F# Team Vision | Dev11 Experience | Feature Name | Stack Rank | Description | Pri | Area | Dev % Done | QA % Done | Rough Dev Cost | Rough QA Cost | Dev Cost | QA Cost | Milestone | Dev FC Weeks | Dev FC Weeks Remaing 4/30 | QA FC Weeks | Column1 | Costed By | Dev | QA | Notes
Fluent | Dev11 Simpler | Reliable, Quick, Understandable, Fluent Intellisense | 1 | F# Intellisense is fluent and reliable. Intellisense filtering Intellisense context aware. Correctness. Performance. Good enough. Forever. (Beware of danger of in-your-face intellisense) | Critical | IDE support | 0% | 0% | 8 M2
Lang+Data Leader | Lang Leadership, Dev11 Simpler | Type Provider Foundations | 1 | I can write a type provider for F# unit testing, no UI hangs error isolation target multiple platforms TODO scrubbing specs & full design scrubbing code reviews threat model | Critical | Compiler | 50% | 20% | 6 M2 2 M3
Fluent | Dev11 Simpler | Better Editing | 4 | Finish parameter help, improved quick info, Quick search, vertical guidelines | Value Add | IDE support | 0% | 0% | 6 M2
Fluent | Dev11 Simpler | Full Query Support | 4 | seq { ...orderby/groupby/join... } query { ...orderby/groupby/join... } general LINQ query patterns (query syntax -> LINQ code gen for expression trees) F# Queries are on par with LINQ, Nullable Note: debugging experience is important Note: design work needed urgently here | Value Add | Language/ Compiler | 0% | 0% | 6 M2
Fluent | Dev11 Simpler | Fluent Debugger Experience | 4 | F# Debug Experience: watch namespaces, data tips paths | Value Add | IDE Support | 0% | 0% | 2 M2
Opportunity | Win8 | Viable on Win8 | 1 | F# can build Win8 applications, NoPIA, Align with C# async (interop, perf, debug,) | Critical | Compiler |  |  | 8 M3
Lang+Data Leader | Lang Leadership, Dev11 Simpler | Data Access | 5 | Type Provider for OData, SQL, WSDL | Value Add | Library |  |  | 4 M3
Fluent | Dev11 Simpler | Known State for VS Assets through DTE Limitations and Investments | 4 | Aim: known state for [ Xaml/Jupiter, Dbml ] designers. Tested and working for existing Phone, Silverlight, Win8, WPF, SQL templates. No great expansion in scope of design experience. Work: End-to-end scenario testing, project system extensibility point completions, or limitations. | Value Add | IDE Support | 0% | 0% | 4 M3 | x2
Fluent | Dev11 Simpler | Language Improvements | 6 | Aim: Simplicity and Fluency of Design & Coding, Remove Adoption Blocker, Remove Barrier to Entry Recursive Groups (within files, across files) | Value Add | Language |  |  | 4 M3
Fluent | Dev11 Simpler | Compiler Error Message Improvement | 4 | F# Error Messages are 3 times better, Ideal Error List | Value Add | Compiler |  |  | 4 M3
Fluent | Dev11 Faster Leaner | Project Build Performance | 6 | F# Project Build is 20% faster | Value Add | Compiler | 0% | 0% | 6 M3 | lo
|  | Tax | 4 | Portable (M), Round-tripping (0-S), SL5 |  |  |  |  | 2 M2 2 M3
Out Of Band
Lang+Data Leader | Lang Leadership | OSS Release, Academic | 1 |  | Critical | Community |  |  | 8 MSR
Lang+Data Leader | Lang Leadership | Free Tool MSI Updates, Mono Testing | 1 |  | Critical | Community |  |  | 2 | x2
Fluent | Dev11 Simpler | Simple End-to-end Experience | 4 | [ Web, Cloud/Azure, Phone, Win8, DesktopApps ]. App building, online templates, test methodology | Value Add | Deployment |  |  | 4
Opportunity | Dev11 Simpler | Great on the Phone | 4 | Templates, messaging, samples, screencasts, smaller FSharp.Core | Value Add | Community |  |  | 4
Opportuntity | Dev11 Simpler | Great on Azure | 4 | Templates, messaging, samples, screencasts, smaller FSharp.Core | Value Add | Community |  |  | 2
Cut Line
|  | FSharp.Core in .NET 4.5 | 10 | Put it in the Framework (Full or Client? Silverlight?) | Cut
|  | Project Service Improvements | 10 | Folders, DragAndDrop | Cut | IDE Support
|  | Common Project System | 10 | Move F# to CPS | Cut | IDE Support
|  | Templates in the Box | 10 | F# has the templates I need in the box | Cut | VS Experience | 0% | 0%
|  | Code Focused | 10 | F# supports colorization | Cut | IDE support | 0% | 0%
|  | F# Express | 10 | Free Supported F# IDE | Cut | Setup/Release | 0% | 0%
|  | Web Site project support | 10 | WebSite F#-only designer and project support | Cut | IDE support | 0% | 0%
|  | Full Xaml/WPF Project support | 10 | Full F#-only Xaml Designer + WPF F#-only project support | Cut | IDE Support | 0% | 0%
|  | WinForms designer | 10 | Winform designer and project support | Cut | IDE support | 0% | 0%
|  | Advanced extensibility | 10 | An F# language model and hooks to build refactorings, tools, etc. The ability to build a 3rd party F# IDE. Extensibility hooks in FSI & Project System | Cut | IDE support | 0% | 0%
|  | Additional Visual F# Interactive Features | 10 | Debuggabitlity, Intellisense, Colors, Send project references to FSI. Send source from FSI to the editor. | Cut | Debugger | 0% | 0%
|  | WCF Service References and other Single File Generators | 10 | Add new Service Reference, LINQ to SQL, References and Settings, etc. | Cut | IDE Support | 0% | 0%
|  | Advanced Debugging | 10 | Allow using F# in the immediate window instead of C#. | Cut | Debugger | 0% | 0%
|  | Class View/Object Browser support F#-style display | 10 |  | Cut | IDE support | 0% | 0%
|  | Advanced Code Focused Features | 10 | Refactoring, Navigation, outlining, formatting, Tools¦Options, TODO support, Live Intellisense, snippets, Project to project references give live information | Cut | IDE support | 0% | 0%
|  | Engineering Investments | 10 | Long term sustainability investments/refactorings | Cut | All over
|  | Hosted Execution (Hosting API) | 10 | NOTE: replaced by OSS release | Cut | Compiler
|  | Supported Language Service API | 10 | NOTE: replaced by OSS release | Cut
Note on D2: Luke Hoban: Seperately stack ranked for CTP and RTM. CTP is timeboxed to end 9/1.
Note on F2: Luke Hoban: Priority: - 1 = Bone Line - 2 = Current Plan - 3 = Cut - 4 = Very Cut
Note on H2: Luke Hoban: % to code complete.
Note on I2: Luke Hoban: % to test complete
Note on L2: Luke Hoban: Costs in "Feature Crew Weeks". Conversion factor from heads down time is ~ x5. So numbers can also be read as "Heads down coding days".
Note on M2: Luke Hoban: Costs in "Feature Crew Weeks". Conversion factor from heads down time is ~ x5. So numbers can also be read as "Heads down coding days".
Note on F22: Luke Hoban: Was 2 - need more data from Brian.
Note on F23: Luke Hoban: Was 2 - need more data from Brian.
Note on F24: Luke Hoban: Was 2 - need more data from Brian.
Note on F25: Luke Hoban: Was 2 - need more data from Brian.
Note on F28: Luke Hoban: Was 2 - need more data from Brian.
Note on F29: Luke Hoban: Was 2 - need more data from Brian.
Note on F30: Luke Hoban: Was 2 - need more data from Brian.
Note on F31: Luke Hoban: Was 2 - need more data from Brian.
Note on F32: Luke Hoban: Was 2 - need more data from Brian.
Note on F33: Luke Hoban: Was 2 - need more data from Brian.
Note on F34: Luke Hoban: Was 2 - need more data from Brian.
Note on F35: Luke Hoban: Was 2 - need more data from Brian.
Note on F36: Luke Hoban: Was 2 - need more data from Brian.
Note on F37: Luke Hoban: Was 2 - need more data from Brian.
Note on F38: Luke Hoban: Was 2 - need more data from Brian.
Note on F39: Luke Hoban: Was 2 - need more data from Brian.
Note on F40: Luke Hoban: Was 2 - need more data from Brian.
Note on D72: Luke Hoban: Seperately stack ranked for CTP and RTM. CTP is timeboxed to end 9/1.
Note on F72: Luke Hoban: Priority: - 1 = Bone Line - 2 = Current Plan - 3 = Cut - 4 = Very Cut
Note on H72: Luke Hoban: % to code complete.
Note on I72: Luke Hoban: % to test complete
Note on L72: Luke Hoban: Costs in "Feature Crew Weeks". Conversion factor from heads down time is ~ x5. So numbers can also be read as "Heads down coding days".
Note on M72: Luke Hoban: Costs in "Feature Crew Weeks". Conversion factor from heads down time is ~ x5. So numbers can also be read as "Heads down coding days".
Note on H78: Luke Hoban: Should probably say this is 50% done or so….
Note on F89: Luke Hoban: Was 2 - need more data from Brian.
Note on F90: Luke Hoban: Was 2 - need more data from Brian.
Note on F95: Luke Hoban: Was 2 - need more data from Brian.
Note on F96: Luke Hoban: Was 2 - need more data from Brian.
Note on F97: Luke Hoban: Was 2 - need more data from Brian.
Note on F99: Luke Hoban: Was 2 - need more data from Brian.
Note on F100: Luke Hoban: Was 2 - need more data from Brian.
Note on F101: Luke Hoban: Was 2 - need more data from Brian.
Note on F102: Luke Hoban: Was 2 - need more data from Brian.

## M3 Staffing
Dev |  | QA | PM
Jomo | 1
Brian | 1
Joe | 1
Don | 1
James | 1

## Bugs
| Total | Code Defect | Suggestions | WorkItems | Other
Compiler | 352 | 277 | 36 | 27 | 12
BinaryGen |  | 5
CodeGen |  | 36
DebugInfo |  | 3
Error Messages |  | 140
Flags |  | 14
Import |  | 2
LexFilter |  | 12
Lexing |  | 7
Metadata |  | 0
Name Resolution |  | 12
NullandDefulat |  | 1
OCamlCompat |  | 0
Optimizations |  | 1
Parsing |  | 11
PAtternCompilation |  | 2
Printing |  | 2
Quotations |  | 1
Subtyping |  | 0
Typecheck Core |  | 6
TypeCheck Objects |  | 16
Units of Measure |  | 6
XmlHtmlDoc |  | 4
Language | 79 | 13 | 37 | 2 | 27
Library | 35 | 24 | 4 | 5 | 2
Perf | 6 | 3 | 1 | 0 | 2
Release | 31 | 23 | 0 | 5 | 3
Testing | 22 | 0 | 0 | 13 | 9
Tools | 77 | 57 | 15 | 2 | 3
VS Plugin | 257 | 200 | 36 | 21 | 0
Debug | 41 | 15
LanguageService | 151 | 125
ProjectSystem | 86 | 60
Total | 1137 | 597 | 129 | 75 | 336